## Guideline
GUIDELINE OF Q&A MANAGEMENT SHEET
1. Purpose
Q&A Management Table is to record and follow up the questions and answers communicated between project team
and the customer. All the questions/confirmation noted in emails, raised in meetings (TV meeting, meeting with
onsiter from customer side) shall be logged and tracked here.
Project must define one person-in-charge to take care of Q&A management in the project to avoid duplicate Q&A
or unnecessary clarification at the beginning of project. Normally; this is project PTL/PM. It is recommended not
to put for more than one question into one Q&A because it may make the people confuse and miss the points.
If the file's size is too big, it could be separated into several files. In that case, a sequential number (01, 02, etc.) is
added to the end of the file name.
2. Scope
Application to all FSOFT departments/projects
3. Definition & Criteria
No. is the number of the question
Question is Content of the question. If there is a feedback or further clarification about the same question, use the following format: [yyyy/MM/dd Your Company/Customer Name/PersonName Add] For example: We don't understand XYZ. [2006/12/19 FPT add] Following your suggestion, we still cannot... Note that the latest addition is in red so that the involved parties can easily notice it.
Answer is the response to the question. If there is further discussion, use the same rules as specified for Question
Priority High - if it blocks the work. Medium - if an answer is needed within 2-4 days. Low - Cosmetic question
Created On - Date on which the question is raised. Filled in by Your company
Created By - The person who asks the question
Assigned to - The person who's in charge of answering the question. Filled in by the customer
Deadline - The date expected to receive the answers for the question
Answered on - The date on which the question is actually answer, expected to be filled by the customer
Status Open: The question has not been answered Closed: The question is satisfactorily answered Canceled: Question is canceled In progress: the answer is available but not fully satisfied
Conclusion - a place for a conclusion. Conclusion must be more specific/detail and clear to understand about what FPT understands finally and what FPT will do.
Question Type - Type of the question: Clarification - Ask for explanation about points/issues FPT don't fully understand Confirmation - Ask the customer to confirm a solution proposed by FPT Customer Defect - The issue referred by the question is a customer's defect.
Process specifies process/activities for which the question raised. This category could be customized by projects to fit their need. In normal case, it contains:
Requirement: questions on user requirements, Functional specification or GUI prototype
Design: questions on design, system architecture, detail designs
Coding: questions on coding, coding convention, coding techniques
Deployment: questions on deployment, deployment environments, installation, etc
Test: questions on Test point of view, Test cases, Test plan, Test report, Test data, etc.
Project management: questions on project scope, acceptance criteria, schedule, effort change, working procedures, etc…
4. Procedure of Q&A Management
FPT
Customer
PM

## Q&A Management Sheet
Q&A Management Sheet
| Project Code: | T&L Project
| Q&A Manager: | Tuan-Thanh Phan
| Last updated date | 2021-11-20
No of Open items
No of In progress items
No of Closed items
No of Cancelled items
Total
No | Question |  | Answer | Priority | Created On | Created By | Assigned To | Deadline | Answered On | Status | Conclusion | Question Type | Title | Process
1 |  |  |  | High | 2025-09-18 23:06 | Tuan-Thanh Phan |  |  | s | Open |  | Confirmation |  | Requirement
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18